## TRACKER
Project Development and Completion Tracker
Porject ID:
Project Start Date: 29-07-23 Project End Date:
Product Description - Developing a web-based expense tracker application to help users manage and monitor their finances efficiently.
| Name of Team member | Designation |  | Name of Students |  | Role |  | Name | Designation
Project Architech Team Members |  |  | Project Development Student Team Memebers |  |  | Team Lead | Project Domain Expert Team Members (Geolife)
Frond End
Team Lead
Front/Back End
Team Lead
Back End
Front End
Epic: | As a user, I want to be able to track and manage my expenses efficiently using the wallet app.
User Registration and Authentication | As a user, I want to create an account and log in securely to access the wallet app
Expense Entry and Categorization | As a user, I want to be able to enter my expenses, specifying the amount, date, and category (e.g., groceries, transportation).
Expense Visualization | As a user, I want to see visual representations of my expenses, such as charts or graphs, to understand my spending patterns.
Export and Repots | As a user, I want to export my expense data or generate reports for tax purposes or financial planning.
Currency and Conversion | As a user, I want to be able to track expenses in different currencies and have them converted to my primary currency.
Transction Histroy | As a user, I want to view a history of my past transactions, including details like date, category, and payment method.
Budget Setting and Tracking | As a user, I want to set monthly budgets for different expense categories and receive notifications when I approach or exceed my budget
Task1: | Design User Registration Layout with Database Configuration
Task2: | Design login page layout.
Task3: | Design Dashboard Layout
Task4: | Design Expense Entry Layout
Task5: | Design Expense Categorization Layout
Task6: | Design Budget Setting Layout
Task7 | Design Transaction Histroy Layout
Task 8: | Design Currency Conversin Layout
Task9 | Design Export and Report Layout
ACCEPTANCE CRITERIA
1 | Users can successfully register by providing their name, email, and password. | [9 empty] | Not Started | Medium
2 | Registered users can log in using their email/username and password.
3 | The dashboard displays the user's current wallet balance. | [9 empty] | In Progress | Low
4 | Users can enter expenses, specifying the amount and date, and submit them.
5 | Users can categorize their expenses into predefined categories or create custom categories. | [9 empty] | Complete | High
6 | Users can set monthly budgets for different expense categories, and the app provides notifications when they approach or exceed the budget limits.
7 | Users can view a list of past transactions, including details like date and category.
8 | Users can select different currencies and view expense amounts converted accurately. | [9 empty] | On Hold
9 | Users can export their expense data in a downloadable format (e.g., CSV, PDF) for analysis and reporting. | [9 empty] | Overdue
SPRINT NO. | TASK NAME | SUB TASKS | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status | Priority
SPRINT 01 : Website Interface Design | User Registration and Login Pages | Define layout wireframes and visual elements. | Complete- | Akshay,Unmesh | 2023-09-06 | 2023-09-15 | 2023-09-06 |  | 100% | High
|  | Create a mockup of the registration page. | Complete | Akshay,Unmesh | 2023-09-06 | 2023-09-16 | 2023-09-06 |  | 85% | High
|  | Review and finalize the design with the team. | Complete | Akshay,Unmesh | 2023-09-06 | 2023-09-25 | 2023-09-10 |  | 50% | High
| User Login Page Layout | Define layout wireframes and visual elements. | In Progress | Akshat,Akshay | [5 empty] | Medium
|  | Create a mockup of the login page. | In Progress | Om,,Akshat | [5 empty] | Medium
|  | Review and finalize the design with the team. | In Progress | Om,,Akshat | [5 empty] | Medium
| Style Guide Creation | Develop a visual style guide for the website. | Not Started | Akshay,Om | [5 empty] | Low
|  | Specify color schemes, typography, and UI components. | Not Started | Akshat | [5 empty] | Low
|  | Ensure consistency in design elements (buttons, forms, headings). | Not Started | [6 empty] | Low
| Dashboard Wireframes | Create wireframes for the dashboard layout. | Not Started | [6 empty] | Low
|  | Include placeholders for wallet balance and future features. | Not Started | [6 empty] | Low
|  | Collaborate with the team to refine the wireframes. | Not Started | [6 empty] | Low
| Wallet Balance Display | Implement the display of the user's wallet balance. | Not Started | [6 empty] | Low
|  | Ensure that the balance is retrieved from the database. | Not Started | [6 empty] | Low
|  | Design and integrate visual elements for the balance. | Not Started | [6 empty] | Low
| Placeholder Design | Create design placeholders for future dashboard features. | Not Started | [6 empty] | Low
|  | Include placeholders for transaction history, expense entry, and more. | Not Started | [6 empty] | Low
|  | Ensure that the placeholders maintain a consistent design style. | Not Started | [6 empty] | Low
SPRINT 02: Website Interface Refinement and Expense Entry Categorization
| Enhanced User Registration and Login Pages | Subtask 3.1: Implement user registration logic.
Subtask 3.2: Implement user login logic.
Subtask 3.3: Ensure responsive design for various devices.
| Dashboard Functionality | Subtask 4.1: Retrieve and display recent transactions.
Subtask 4.2: Implement dynamic wallet balance updates.
Subtask 4.3: Add placeholders for budget and reports sections.
| Design Expense Entry Layout | Subtask 5.1: Design an expense entry layout.
Subtask 5.2: Implement expense entry functionality.
Subtask 5.3: Ensure user-friendly input validation.
| Design Expense Categorization Layout | Subtask 6.1: Design an expense categorization layout.
Subtask 6.2: Allow users to categorize expenses.
Subtask 6.3: Implement category selection and management
SPRINT 03 : Finalize Interface and Prepare for Backend Integration
| Budget Setting Layout | Subtask 7.1: Design a budget setting layout.
Subtask 7.2: Allow users to set monthly budgets.
Subtask 7.3: Implement placeholders for budget notifications.
| Export and Reports Section Layout | Subtask 9.1: Design a layout for exporting data and generating reports.
Subtask 9.2: Prepare the interface for future export and reporting functionalities.
Subtask 9.3: Ensure overall design consistency.
| Currency Conversion (if applicable) | Subtask 8.1: Create a currency conversion layout. | On Hold
|  | Subtask 8.2: Implement basic currency selection. | On Hold
|  | Subtask 8.3: Ensure smooth user interactions | On Hold
| Backend Setup and Integration | Subtask 10.1: Select and set up backend technologies (e.g., Django, Flask).
Subtask 10.2: Establish database schemas for expenses, users, and settings.
Subtask 10.3: Implement API endpoints for frontend-backend communication.
Subtask 10.4: Ensure secure data storage and transmission.
Subtask 10.5: Perform integration testing to validate frontend-backend interactions

## Student Team
STUDENT INTERN LIST
Sr. No. | Name of Inern | Email Address | Contact | class | Domain (Web, App, Backend)
1 | Prajwal Sah | prajwalsah212@gmail.com | 7776012981 | FY IT DA | ML
2 | Shriya Dilliwale | anitashriya12@gmail.com | 7559361354 | FY IT DA | Flutter, ML | Version 1
3 | Nikhil Chavan | nikhilchavan407@gmail.com | 8369686747 | FY IT - CORE | Flutter | Version 1
4 | Vipul Kumar Singh | vipulkumarbhore@gmail.com | 7764059016 | FY IT - CORE | Flutter | Version 2
3 | Anjali Bhatt | anjalibhatt601@gmail.com | 830811254 | FY CSE Core 2 | Flutter, ML | Version 1
4 | Shruti Singasane | singasane.shruti2001@gmail.com | 8652233102 | FY CSE Core 2 | Flutter, ML | Version 1
5 | Rushil Jain | rushiljain2001@gmail.com | 9371775841 | FY CSE IS 1 | Flutter, ML | Version 1
7 | Sumeet Sapkal | sumeetspkl@gmail.com | 9112156784 | FY CSE | Flutter, MySQL | Version 2
8 | Sunny Yadav | sunnyyadavtheone@gmail.com | 7878964402 | FY CSE | Flutter, MySQL | Version 2
9 | Siddhant Oswal | oswalsiddhant2001@gmail.com | 8329979013 | FY CSE | Flutter | Version 2
10 | Simon Singh | simonsinghdomain@gmail.com | 7470659108 | FY CSE | Flutter | Version 2
11 | Varun Kapse | varunkapse07@gmail.com | 8830624385 | FY IT - PASSED | ML | Version 2
13 | Rutvi Nair | rutvinar305098@gmail.com | 8141393918 | TY CSE IS 1 | Flutter | Version 2